## Sheet1
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
weeks | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | Exams |  |  | Hoildays |  |  | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26
1.1
1.2
1.3
2.1
2.2
2.3
3.1 | bar: 2021-02-01 to 2021-02-08
3.2
3.3
3.4
3.5 | bar: 2021-02-01 to 2021-02-08
4.1 | bar: 2021-02-08 to 2021-02-22
4.2 | bar: 2021-02-15 to 2021-03-01
4.3 | bar: 2021-03-01 to 2021-03-15
4.4
4.5 | bar: 2021-03-15 to 2021-04-26
1.1 | Ethics form signed and approval.
1.2 | Requirements identification and specification of this project.
1.3 | Articles reading and accomplishment of proposal.
2.1 | Decision of the format and content of database.
2.2 | Further articles and websites reading to find useful voice recognition and nlp libraries or API.
2.3 | User interface design for the software.
3.1 | Collection of doctor diagnose prescription and/or conversation contents online for creation of audio type dataset.
3.2 | Development of user interface of EHR form with all basic functions provided.
3.3 | Implementation and combination of speech recording, voice recognition, and Chinese language processing.
3.4 | Interim report writing and validation.
3.5 | Classification of keyword from the result of Chinese language processing.
4.1 | Test on speech recording, voice recognition, and Chinese language processing functions.
4.2 | Test on the performance of keyword classification.
4.3 | Test on the application interaction.
4.4 | Maintenance of repository, implementation of advanced function and optimization of the code.
4.5 | Final report writing and validation.